## Cover Page
https://www.everlightradiology.com/
Everlight - Test Summary Report
| Delivered Build | 1
| Date Reported: | 2023-10-23
| Prepared by: | Huong (Harry) Nguyen
TABLE OF CONTENTS
| No | Sheet
| 1 | Test Summary
| 2 | Defect Summary
| 3 | Test Case Summary
| 4 | Test cases

## Test Summary
Everlight - Testing Summary Report
Release Criteria vs Actual
Defect Severity | Total | Resolved | Open | % Resolved | Criteria
Legacy Defects
Legacy Defects | 0 | 0 | 0 | #DIV/0! | 100%
Defects Found During Test Cycle
Fatal | 0 | 0 | 0 | #DIV/0! | 100%
Major | 0 | 0 | 0 | #DIV/0! | 100%
Minor | 1 | 0 | 1 | 0% | 70%
Cosmetic | 0 | 0 | 0 | #DIV/0! | 50%
Test Case Summary
Passed | 4
Failed | 1
Blocked | 0
Not Run | 0
Not Completed | 0
Total | 5
Execution Percentage | 100%
Builds Under Test
Build Description | Build Number | Date Received | Start Date | End Date | Comments
Environments/Platforms Under Test
Environments/Platforms Under Test |  | Comments
Edge and Chrome

## Test Case Summary
Everlight - Release 1.0 - Test Case Summary
ID | Name | Test Case Description | Priority | Defect ID | Tester | Overall Result | Comment
Create/edit Order
TC-001 | Create order with missing information | Creating a new order that misses one or more required info | Medium |  | Huong Nguyen | Pass
TC-002 | Create a new order with an existing Patient MRN | Create a new order with an existing Patient MRN | High | Jira-0001 | Huong Nguyen | Fail
TC-003 | Create new order, the status is automatically set to SC and Site ID is filtered based on Organization | Create new order, the status is automatically set to SC and Site ID is filtered based on Organization | Medium |  | Huong Nguyen | Pass
Cancel Assession Numbers
TC-004 | No accession is canceled | No accession is canceled when selecting Cancel from the confirmation message | Low |  | Huong Nguyen | Pass
TC-005 | Assession number is canceled | Assession number is canceled | Medium |  | Huong Nguyen | Pass

## Test cases
Revision History
Date | Sheet Name | Version | Description | Designer/Reviser | Reviewed By | Approved By | Approved Date
2023-10-22 | Test cases | 1 | Design test cases | Huong (Harry) Nguyen | Huong (Harry) Nguyen
Overal of Test result
Build Number | Passed | Failed | Blocked | Not Run | Not Completed | Not Planned
Edge | 4 | 1 | 0 | 0 | 0 | 0
Chrome | 4 | 1 | 0 | 0 | 0 | 0
ID | Name | Test case description | Precondition | Step name | Step description | Expected Result | Defect ID | Edge |  | Chrome |  | Note
[8 empty] | Step | Case | Step | Case
Create/Edit Orders
TC-001 | Create order with missing information | Creating a new order that misses one or more required info | The site is launched successfully on the target environment | Step 1 | Launch the site in browser | The site launched successfully |  | Passed | Passed | Passed | Passed
|  |  |  | Step 2 | Click on Orders | Orders list and Create New display |  | Passed |  | Passed
|  |  |  | Step 3 | Click on Create New | New Order page displays |  | Passed |  | Passed
|  |  |  | Step 4 | Leave all the field blank and click Submit | Red text displays showings the fields are required |  | Passed |  | Passed
|  |  |  | Step 5 | Enter a value in any field and click Submit | The field with value is not validated as required due to empty field |  | Passed |  | Passed
|  |  |  | Step 6 | Click Cancel | The New Order page closes and no order is being created and system moves back to the orders list page |  | Passed |  | Passed
TC-002 | Create a new order with an existing Patient MRN | Create a new order with an existing Patient MRN | 1. The site is launched successfully on the target environment 2. There's at least one order in the orders list with a valid MRN | Step 1 | Launch the site in browser | The site launched successfully |  | Passed | Failed | Passed | Failed
|  |  |  | Step 2 | Click on Orders | Orders list and Create New display |  | Passed |  | Passed
|  |  |  | Step 3 | Record an MRN and Patient Name | The MRN is recorded MRN____________P312_________ Patient Name:_______Tony Jenkins___________ |  | Passed |  | Passed
|  |  |  | Step 4 | Click on Create New | New Order page displays |  | Passed |  | Passed
|  |  |  | Step 5 | Enter the MRN recorded at step #3 | The MRN is entered |  | Passed |  | Passed
|  |  |  | Step 6 | Enter First Name and Last Name that are different from the ones recorded at step #3 | First Name and Last Name are entered |  | Passed |  | Passed
|  |  |  | Step 7 | Enter/Select info for the rest of fields | The info entered/selected for the rest of the fields |  | Passed |  | Passed
|  |  |  | Step 8 | Click Submit | The new order page closes and new order is created |  | Passed |  | Passed
|  |  |  | Step 9 | Go to the orders list and verify that the new order is created successfully with the info entered/selected at step #5,#6 and #7 | The newly created order with the patient name recorded at step #3 instead of the name entered at step #3 The other info of the order display correctly | Jira-0001 | Failed |  | Failed
TC-003 | Create new order, the status is automatically set to SC and Site ID is filtered based on Organization | Create new order, the status is automatically set to SC and Site ID is filtered based on Organization | The site is launched successfully on the target environment | Step 1 | Launch the site in browser | The site launched successfully |  | Passed | Passed | Passed | Passed
|  |  |  | Step 2 | Click on Orders | Orders list and Create New display |  | Passed |  | Passed
|  |  |  | Step 3 | Click on Create New | New Order page displays |  | Passed |  | Passed
|  |  |  | Step 4 | Enter/Select info for all required fields Verify Site ID is filtered based on the selection of Organization | The info entered/selected successfully for all required fields Site ID is filtered based on the selection of Organization |  | Passed |  | Passed
|  |  |  | Step 5 | Click Submit | The new order page closes and new order is created |  | Passed |  | Passed
|  |  |  | Step 6 | Verify the Status of the newly created order displays as SC | The Status of the newly created order displays as SC |  | Passed |  | Passed
Cancel Assession Numbers
TC-004 | No accession is canceled | No accession is canceled when selecting Cancel from the confirmation message | 1. The site is launched successfully on the target environment 2. There is at least one or more orders in the orders list | Step 1 | Launch the site in browser | The site launched successfully |  | Passed | Passed | Passed | Passed
|  |  |  | Step 2 | Click on Orders | Orders list and Create New display |  | Passed |  | Passed
|  |  |  | Step 3 | Locate an order in the orders list and click on X button in the Status column | A message displays showing the confirmation of canceling of the selected assession number with OK and Cancel buttons |  | Passed |  | Passed
|  |  |  | Step 4 | Click on Cancel | The message closes and no accession number is canceled |  | Passed |  | Passed
TC-005 | Assession number is canceled | Assession number is canceled | 1. The site is launched successfully on the target environment 2. There is at least one or more orders in the orders list | Step 1 | Launch the site in browser | The site launched successfully |  | Passed | Passed | Passed | Passed
|  |  |  | Step 2 | Click on Orders | Orders list and Create New display |  | Passed |  | Passed
|  |  |  | Step 3 | Locate an order in the orders list and click on X button in the Status column | A message displays showing the confirmation of canceling of the selected assession number with OK and Cancel buttons |  | Passed |  | Passed
|  |  |  | Step 4 | Click on OK | The message closes and the selected order/assession number was removed from the orders list |  | Passed |  | Passed

## Defect Summary
Everlight - Release 1.0 - Defect Summary
New Defects Found in the Test
Severity | Total | Resolved
Fatal | 0 | 0
Major | 0 | 0
Minor | 1 | 0
Cosmetic | 0 | 0
Priority | Total | Resolved
High | 1 | 0
Normal | 0 | 0
Low | 0 | 0
Status
Open | 1
Re-opened | 0
In Progress | 0
Resolved | 0
Verified | 0
Closed | 0
Resolution
Fixed | 0
Do Not Fix | 0
Duplicate | 0
Need more information | 0
Cannot Reproduce | 0
Pending Outside Support | 0
Cannot Fix | 0
Future Candidate | 0
Legacy Defects to be fixed
Status | Resolved
Resolved | 0
Verified | 0
Closed | 0
Reopened | 0
Total | 0

## Defect Data
Everlight - Release 1.0 - Defect Data
Key | Summary | Defect Type | Reporter | Assignee | Severity | Priority | Status | Resolution | Affect Version/s | Fix Version/s | Components | Created | Updated
Jira-0001 | Blank Site Name displays in the orders list after a new order created with Site ID as Clinic. See screenshot | UI | Huong (Harry) Nguyen | Developer 1 | Minor | High | Open |  | 1 |  | Create New Order | 2023-10-23

## Screenshots
JIRA-0001: